## Gantt Chart Template
Project Timeline Template
Project Name: Timer IP
| Task Name | Start (Date) | End (Date) | Duration (Days) | %done | Column1
[5 empty] | %done | Stuck point
| Investigation | 2025-07-16 | 2025-07-19 | 3 | 100
| Design specification | 2025-07-20 | 2025-07-26 | 7 | 100
| RTL coding | 2025-07-27 | 2025-08-02 | 7 | 100
| Compilation | 2025-08-03 | 2025-08-04 | 2 | 100
| Verification Plan | 2025-08-05 | 2025-08-11 | 7 | 100
| Build env | 2025-08-05 | 2025-08-06 | 2 | 100
| 1Pass | 2025-08-07 | 2025-08-09 | 3 | 100
| All Pass | 2025-08-10 | 2025-08-16 | 7 | 100
| Coverage | 2025-08-17 | 2025-08-19 | 3 | 100
| Total |  |  | 34 | 100
Formulas:
End (Date) = [Start (Date)]+[Duration (Days)]
End (Date) = [Start (Date)]+[Duration (Days)]-1
Start (Date) = [End (Date), row above]+1
Start (Date) = [Start (Date), row above]
Note on B13: PC: Understand all function + Register bit/field: 20% + Counter: 20% + Counting mode: 20% + APB: 30% + interrupt: 10%
Note on B14: PC: Design specification making + Feature list: 10% + Block diagram: 10% + IO port list: 10% + Waveform: 30% + Logic diagram: 40%
Note on B15: PC: Calculate % based on your block diagram. For example, your module has 5 block --> each block can be 20%. Note that % for each block can be differ based on your estimation.
Note on B16: PC: Compile DUT only: 50% Write 1 simple tb, instantiate DUT and run 1 simulation (no stimulus) without Warnings/Errors: 50%
Note on B17: PC: Write verification plans to cover all features of the design. The % based on your estimation.
Note on B18: PC: Build necessary components for your env: APB master, checkers, scripts, report...
Note on B19: PC: 1PASS scenario (sanity test): a testcase that cover some basic functions of the design 1. Write 0xffff to TCMP0 and read back 2. Enable interrupt 3. Start timer 4. Check if interrupt can be asserted when timer reaches TDR0 value.
Note on B20: PC: %done is calculated based on how many items already passed in your verification plan
Note on B21: PC: Toggle: 20% Statement: 20% Expression: 20% Condition: 20% Branch: 20%

## feature list
FEATURE LIST
Timer IP module is customized from CLINT module of RISC-V architechture Timer support 64 bit count up counter, low active arsync reset. Support timer interrupt Advanced level: + Support halt in debug mode + Support APB 32 bit transfer to configure. Support wait state , byte access, error handling 12 bit address Counter support 2 counting mode +Default mode: counting speed depend on system clock + Control mode: counting speed can be controlled by setting registers -Counter continues counting when interrupt occurs. Counter is cleared to initial value when timer_en changes from H to L. When it changes from L to H agian, counter count normally

## Block diagram
x

## waveform
APB no wait state
APB wait state
counter control mode
Halt mode
Interrupt

## logic diagram
TCR
interrupt
CNT_CTRL
COUNTER
TDR
TCMP

## Vplan
ID | Item | Sub item 1 | Sub item 2 | Test sequence | Pass condition | pat name | Result
1 | RESET | Init |  | After reset is asserted, perform read acces to TCR TDR0/1, TCMP0/1 TIER, TISR, THCSR, read back and compare | Read value is default value TCR=0x100 TDR0/1,TIER,TISR,THCSR=0x0 TCMP0/1 =32'hFFFF_FFFF | reset_verify.v | PASS
2 |  | while counting |  | After reset is released, write 0x1 to TCR to start counting . Wait for a while then assert reset . Perform read access to TCR, TCD0/1, TCMP0/1 TIER,TISR,THCSR, read back and compare | Read value is default value TCR=0x100 TDR0/1,TIER,TISR,THCSR=0x0 TCMP0/1 =32'hFFFF_FFFF | reset_verify.v | PASS
3 | REGISTER ACCESS | TCR | reset value check | After system reset is released, perform read access to TCR | Read value=0x0000_0000 | TCR_access | PASS
4 |  |  | R/W access | 1.Write 0x0000_0000 & read back and compare 2.Write 0xFFFF_FFFF & read back and compare 3.Write 0x5555_5553 & read back and compare 4.Write 0xAAAA_AAAA& read back and compare | 1.read value= 32'h0000_0000 2.read value=32'h0000_0000 3. read value=32'h0000_0503 4.read value=32'h0000_0502 | TCR_access | PASS
5 |  |  | Special access for div_val | Write wdata[11:8]={8,9,7} | 1.pslverr=0 and read value based on write value 2.pslverr=1 and not write wdata to register file 3.pslverr=0 and read value based on write value | TCR_access | PASS
6 |  |  | Check timer_en | Change value of timer_en from H to L | TDR0/1=32'h0 | TCR_access | PASS
7 |  | TDR | Check value of register when timer_en changes from H to L | when timer_en=1 changes to timer_en=0 & read back and compare | Read value=32'h0000_0000 | TDR_access | PASS
8 |  |  | R/W access | 1.Write 0x0000_0000 & read back and compare 2.Write 0xFFFF_FFFF & read back and compare 3.Write 0x5555_5555 & read back and compare 4.Write 0xAAAA_AAAA& read back and compare | 1.read value= 32'h0000_0000 2.read value=32'hFFFF_FFFF 3. read value=32'h5555_5555 4.read value=32'hAAAA_AAAA | TDR_access | PASS
9 |  |  | reset value check | After system reset is released, perform read access to TDR | read value=0x0000_0000 | TDR_access | PASS
10 |  |  | Write access , tim_en=0 | Set timer_en =0, write wdata to TDR0/1 and read back | Written value matches | TDR_access | PASS
11 |  |  | Write access, timer_en = 1 | Set timer_en =1, write wdata to TDR0/1 and read back | Value not changes, | TDR_access | PASS
12 |  | TIER | R/W access | 1.Write 0x0000_0000 & read back and compare 2.Write 0xFFFF_FFFF & read back and compare 3.Write 0x5555_5555 & read back and compare 4.Write 0xAAAA_AAAA& read back and compare | 1.read value= 32'h0000_0000 2.read value=32'h0000_0001 3. read value=32'h0000_0001 4.read value=32'h0000_0000 | TIER_access | PASS
13 |  |  | Check enable int_en | Write int_en=1 and compare | int_en=1 occurs interrupt when TCMP=TDR | TIER_access | PASS
14 |  |  | Prohibited write handling | Write when int_en=0 | int_st not affected, tim_int=0 | TIER_access | PASS
15 |  | TISR | Read after interrupt | tim_int=1, read TISR | int_st=1, tim_int stays | TISR_access | PASS
16 |  |  | Clear interrupt | 1. write 1 when int_st=1 2. write 0 when int_st=1 3. write 0/1 when int_st=0 | 1. int_st=0 ,tim_int=0 2. int_st=1, tim_int=1 3. int_st=0, tim_int=0 | TISR_access | PASS
17 |  | THCSR | reset value check | After reset system, read back | Read value=32'h0000_0000 | THCSR_access | PASS
18 |  |  | check halt mode | 1. write halt_req=1 after debug_mode=1 2. write halt_req=1 when debug_mode=0 | 1. halt_mode=1, halt_ack=1 , counter stop counts 2. halt_mode and halt_ack =0, counter still count | THCSR_access | PASS
19 |  | TCMP | reset value check | Read TCMP | read value =32'h0000_00000 | TCMP_access | PASS
20 |  |  | R/W access | 1.Write 0x0000_0000 & read back and compare 2.Write 0xFFFF_FFFF & read back and compare 3.Write 0x5555_5555 & read back and compare 4.Write 0xAAAA_AAAA& read back and compare | 1.read value= 32'h0 2.read value=32'hFFFF_FFFF 3. read value=32'h5555_5555 4.read value=32'hAAAA_AAAA | TCMP_access | PASS
21 | Functional Verifivation | COUNTER | Enable count | 1.Write TDR0/1=0, div_val=4, turn on timer_en=1 1.Write TDR0/1=0, div_val=5, turn on timer_en=1 1.Write TDR0/1=0, div_val=6, turn on timer_en=1 1.Write TDR0/1=0, div_val=9, turn on timer_en=1 | 1.Counter increase after 16 system clock 2.Counter increase after 32 system clock 3.Counter increase after 64 system clock 4. Counter does not increase, pslverr occurs | COUNTER_verify | PASS
22 |  |  | Reset during counting | Counter is counting then active rst_n=0 | counter must be =0 | COUNTER_verify | PASS
23 |  |  | Restart from halt | Changes halt_req =1 to halt_req=0 | counter continues counting | COUNTER_verify | PASS
24 |  |  | Overflow | TDR0/1=64'hFFFF_FFFF_FFFF_FFFF -> enable counts readback and compare after 10 cycles | read value: TDR1=0x0 TDR0 is close to 10 value | COUNTER_verify | PASS
25 |  | COMPARE LOGIC | Matching value | 1. Write TCMP0=10, TDR0=9 -> after a period TDR0 =10 2. Write TCMP1 = 0x00000000, TCMP0 = 0xFFFF0000, cnt = TCMP - 1 3.TCMP=0x64 and counter =0x63 | 1.cmp_match=1 at cycle TDR0=TCMP0 2.cmp_match=1 at cycle counter={TCMP1 ;TCMP1} 3.cmp_match=0 |  | PASS
26 |  |  | Match timing | counter= TCMP then the count continue a perid clock | cmp_match =0 after occurs |  | PASS
27 |  |  | Check tim_int in some case | cmp_match=1 but int_en=0 | tim_int not occurs |  | PASS
28 |  | INTERRUPT CONTROL | enable interrupt | Write TCMP=0x05, int_en=1,counter =5 | tim_int=1 when counter=TCMP | INTERRUPT_verify.v | PASS
29 |  |  | Clear by TISR write | tim_in=1 and write 1 to int_st | tim_int =0 when write t to int_st | INTERRUPT_verify.v | PASS
30 |  |  | Disable interrupt | Write TCMP=0x05 , counter=0x05 but tim_en=0 | tim_int=0 interrupt not occurs | INTERRUPT_verify.v | PASS
31 |  |  | Disable int_en when occurs | tim_int=1 and write int_en=0 | tim_int=0 and int_en=0 | INTERRUPT_verify.v | PASS
32 |  | HALT MODE | Checking the condition of halt mode | 1. write debug_mode=1 and halt_req=1 2. write debug_mode=0 and halt_req=1 | 1.Counter stopped, halt_ack =1 2. Counter continue counts, halt_ack=0 | HALT_MODE_verify.v | PASS
33 |  |  | Checking halt_ack and counter after halted | When halt_mode =1 , write 0 to halt_req | Counter counts normally and halt_ack=0 | HALT_MODE_verify.v | PASS
34 |  |  | System reset when halt | halt_req=1 when rst_n=0 | counter reset the value to 0 | HALT_MODE_verify.v | PASS
34 |  |  | write while halt | halt_req=1, counter stop , update new value on TDR0/1 | Counter update new value immediately after TDR0/1 changes | HALT_MODE_verify.v | PASS
35 | APB bus | WAIT STATE | R/W access | After reset is asserted, pstrb=0xF 1.Write 0x0000_0000 to TCMP0, read back and compare 2.Write 0x5555_5555 to TCMP1, read back and compare 3.Write 0xFFFF_FFFF to TCMP0, read back and compare 4.Write 0xAAAA_AAAA to TCMP1, read back and compare 5. ACCESS to IDLE write pwdata=32'hA5A5_A5A5 to TDR0 with write_access_idle task and read_access_idle task to transfer from Access state to Idle state 6. Check penable =0 : After reset, write pwdata=32'h1111_2222 with tim_penable=0 to TCMP0 7. Check psel=0: write pwdata=32'h7777_7777 to TDR0 with psel =0 all the time | Read value is same with write value, pready is high 1 cycle after penable is high 5. Read value was not changed , keep the old value 32'h0000_0000 6. read value =32'hffff_ffff 7. read value=32'h0000_0000 | apb_slave_verify.v | PASS
36 |  | BYTE ACCESS |  | After reset is released 1.Write 0x1111_1111 to TCMP0 with pstrb=0x0,read back and compare 2.Write 0xa5a5_a5a5 to TCMP0 with pstrb=4'b0001, read back and compare 3. Write 0x5555_5555 to TCMP1 with pstrb=4'b0010, read back and compare 4.Write 0xFFFF_FFFF to TDR0 with pstrb=0x3, read back and compare 5.Write 0xAAAA_AAAA to TCMP0 with pstrb =0x4, read back and compare 6. Write 0xBBBB_BBBB to TCMP0 with pstrb=0x5, read back and compare 7.Write 0xCCCC_CCCC to TCMP0 with pstrb=0x6, read back and compare 8.Write 0xDDDD_DDDD to TCMP0 with pstrb=0x7, read back and compare | 1.TCMP0=32'FFFF_FFFF 2.TCMP0=32'hFFFF_ffa5 3.TCMP1=32'hFFFF_55FF 4.TDR0=32'h0000_FFFF 5.TCMP0=32'hFFAA_FFA5 6.TCMP0=32'hFFBB_FFBB 7.TCMP0=32'hFFCC_CCBB 8.TCMP0=32'hFFDD_DDDD | apb_slave_verify.v | PASS
37 |  | ERROR HANDLING |  | After reset is released 1.Write random value (from 0x09 to 0xF) to TCR[11:8]. Read back and compare and write 0x1 to TCR too 2.Write 32'h5555_5451 to TCR, read back and compare 3.Write random value to TCR[11:8], read back and compare 4. Check tcr_div_val when pstrb[1]=0 and write to TCR 5. Check tcr_div_en when pstrb[0]=0 and write to TCR 6. Check pslver when tcr_div_en=1, write pwdata=32'hffff_f2f1 and pstrb=4'b1110 | 1.Read value TCR=0x0000_0100 and pslverr is high 2.Read value of TCR=0x0000_00401 and pslverr is high 3.Read value of TCR 0x0000_0001 and pslverr is high 4. pslverr is low 5. pslverr is high 6. pslverr is high | apb_slave_verify.v | PASS